# Statement of Work (SoW)

Project Title: Northern Ireland Energy Data & Analytics Platform – MVP Development
Client: Strategic Investment Board (SIB)
Sponsor: Department for the Economy (DfE)
Prepared by:
Date:

## 1. Context

Northern Ireland is legally committed to achieving at least 80% of electricity consumption from renewable sources by 2030 under the Climate Change Act (NI) 2022. To meet this target, significant acceleration is required across multiple policy and infrastructure levers, including:

- Grid connection capacity and lead times

- Planning throughput and consenting rates

- Curtailment reduction and constraint management

- Wind development on Forest Service land

- Storage deployment and flexibility services

- Demand electrification (EVs, heat pumps)

- Interconnection capacity and availability

A Strategic Advisor role has been established within SIB to support DfE by ensuring every lever is identified, monitored, and acted upon. This requires a single source of truth for energy data, actionable analytics, and scenario modelling to support Ministers, officials, and delivery partners.

## 2. Objectives

### Primary Objective

Deliver a minimum viable Energy Data & Analytics Platform by 31 March 2026 to enable:

- Live tracking of renewable deployment, grid connections, and demand growth

- Scenario modelling of different pathways to reach 80% RES-E

- Identification of bottlenecks and ownership of key levers

- Evidence-based decision-making for DfE, SONI, NIE Networks, DAERA, DfI, and other stakeholders

### Secondary Objective

Establish a scalable foundation to be expanded in FY 2026/27, adding richer data, advanced analytics, and enhanced visualisation tools.

## 3. Scope of Work

### Phase 1 – MVP Delivery (Sep 2025 → Mar 2026)

#### 3.1. Platform Setup

- Establish a lightweight, cloud-ready Energy Data Lakehouse

- Configure raw, clean, and curated zones (/raw, /clean, /model) with version control.

- Implement automated data pipelines for priority datasets (where possible)

#### 3.2. Data Catalogue & Governance

- Convert the existing data inventory (164 datasets) into a live, searchable data catalogue.

- Assign data owners, stewards, and refresh frequencies.

- Apply data quality scoring (completeness, timeliness, usability).

#### 3.3. Golden Datasets

Prioritise and standardise datasets critical for RES-E delivery:

- Generation & storage pipeline: projects from planning > in-build > operational.

- Grid nodes & hosting capacity.

- Curtailment: historic + simple forecasts.

- Demand projections: EVs, heat pumps, industrial load growth.

- Land suitability: Forest Service parcels + constraints overlays.

- Interconnector milestones.

#### 3.4. Products

- “Path to 80%” Dashboard (v1)

  - KPIs: RES-E %, pipeline MW vs target, build rate, curtailment, consent throughput, grid milestones, land opportunity.

- Scenario Planning Tool (v0)

  - Deterministic model allowing sliders for build rates, consent throughput, connection delays, curtailment %, and demand growth.

- Forest Land Wind Suitability Explorer (v0)

  - Overlay constraints to identify indicative capacity opportunities.

- Governance Framework

  - RACI matrix, refresh SLAs, monthly “data huddles”.

### Phase 2 – Scale & Optimise (Apr 2026 to Mar 2027)

#### 4.1. Data Coverage Expansion

- Automate feeds for planning pipeline, connection queue, and curtailment data.

- Add battery storage, DS3 flexibility services, skills/supply chain capacity metrics.

- Improve data lineage and provenance.

#### 4.2. Advanced Analytics & Modelling

- Curtailment Model v1: zonal PTDF-style approximation.

- Capacity Expansion Model: optimise least-cost portfolios under constraints.

- Demand Growth Microsimulation: EVs/heat pumps saturation by LGD and LV feeder.

#### 4.3. Enhanced Products

- Lever Registry: live view of every delivery lever, owner, status, and impact coefficient.

- Queue Tracker Dashboard: near-real-time monitoring of generation/storage projects and energisation dates.

- Quarterly “Path to 80%” Briefing Pack: narrative + visualisation + actions for decision-makers.

## 4. Deliverables

| Deliverable | Owner | Due Date | Notes |
| --- | --- | --- | --- |
| Energy Data Lakehouse MVP | Data Engineer | Dec 2025 | Raw to clean pipelines in place |
| Data Catalogue & Governance Framework | Analytics Lead | Dec 2025 | With owners & refresh cadences |
| Golden Datasets (v1) | Energy Analyst | Jan 2026 | Pipeline, curtailment, demand |
| “Path to 80%” Dashboard | Analytics Lead | Feb 2026 | Live KPIs & target tracking |
| Scenario Tool (v0) | Modelling Lead | Mar 2026 | Deterministic model |
| Forest Land Suitability Explorer (v0) | Geospatial Analyst | Mar 2026 | Overlay constraints on forest parcels |
| Monthly Data Quality Reviews | Data Stewards | Ongoing | Feed into governance logs |

## 5. Resourcing

| Role | FTE | Purpose |
| --- | --- | --- |
| Product Owner | 0.3 | Define priorities, stakeholder mgmt |
| Data Engineer | 1.0 | Pipelines, ingestion, APIs |
| Analytics Engineer | 1.0 | Golden datasets, dbt, dashboard |
| Energy Analyst | 0.5 | Assumptions, validation |
| Geospatial Analyst | 0.5 | Forest suitability, constraints |
| Modelling Lead | 0.5 | Scenario & optimisation models |
| Delivery Manager | 0.3 | RAID, timelines, governance |

## 6. Timelines & Milestones

| Milestone | Date |
| --- | --- |
| Project Kick-off | Sep 2025 |
| Data Lakehouse MVP Live | Dec 2025 |
| Dashboard & Catalogue v1 | Feb 2026 |
| Scenario Tool v0 | Mar 2026 |
| Phase 1 Completion | Mar 2026 |
| Phase 2 Kick-off | Apr 2026 |

## 7. Dependencies

- External

  - NIE Networks: connection queue, hosting capacity maps

  - SONI: curtailment data, DS3 ancillary services

  - DfI: renewable planning pipeline

  - DAERA/Forest Service: land parcels & constraints

  - Utility Regulator: interconnector timelines, grid cost assumptions

  - NISRA/BEIS: demand & demographics

- Internal

  - Availability of SIB/DfE product owner

  - SME support from SONI, NIE Networks, and DAERA

## 8. Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Data availability delays | High | Prioritise APIs, start with open datasets |
| Dependency on external owners | Medium | Set up steering group, monthly escalation |
| Tooling misalignment | Medium | MS-first strategy unless justified otherwise |
| Modelling complexity creep | Medium | MVP starts simple, iterate in Phase 2 |

## 9. Success Measures

- Operational:

  - 90% of priority datasets ingested, catalogued, and refreshed automatically

  - First “Path to 80%” dashboard live by Feb 2026

- Strategic:

  - Ministers receive actionable scenario insights by Mar 2026

  - Identified delivery levers have clear owners and quantified impacts

- Long-term:

  - Platform reused across energy, planning, environment, and climate policy

  - Reduces time to insight from months to days